## Notes
A stakeholder analysis is a useful tool to organise and understand all impacted groups and individuals associated with a project or a program of work. Stakeholder mapping is an exercise that lets you visualize your relationships with stakeholders. It helps identify those who have power or influence over your project, so you can engage with them effectively. This will help your project to: - Gain more support and resources. - Increase project visibility, especially to executive stakeholders. - Prevent costly roadblocks later in the project cycle. - Communicate through the right channels at the right time. - Share the right level of information with your stakeholders. This begins with brainstorming who your stakeholders are and what their level of involvement is. You’ll need to figure out their interests and goals. Once you have done the stakeholder analysis you can begin on stakeholder mapping. The stakeholder map is just a visual for the information gathered during stakeholder analysis. It literally shows the level of impact and interest for each stakeholder depending on where they land on the map. Once you’ve made the stakeholder map you have a guide to stakeholder engagement. Generally, stakeholder engagement is broken up into three types: informing, consulting and collaborating. The placement of the stakeholders when you’ve done the stakeholder mapping process will then inform how you engage with each of these stakeholders. Stakeholder engagement is how you identify, analyze, plan and implement actions to influence your stakeholders. You determine the needs of your stakeholders and figure out how you’re going to ensure that they’re met. Therefore, the stakeholder mapping process is part of the larger stakeholder engagement process. The term stakeholder management refers to the larger process which includes stakeholder mapping, stakeholder analysis and stakeholder engagement. So stakeholder management relates to every decision a project manager makes in regard to their stakeholders, including the frequency of their meetings and how much project management information they are given. Stakeholder mapping is important because stakeholders are important to the success of a project. There are usually two main stakeholder groups, internal and external stakeholders, who have varied expectations. Without mapping stakeholders in relation to their influence and interest in the project, you’re going to have a hard time communicating with them and keeping them happy. But it’s also a two-way street. Having good communications with stakeholders gives project managers much-needed insight into the project, which helps them in innumerable ways. It helps to mitigate risk and discover the stakeholder’s real goals for the project. In other words, stakeholder mapping is the start of an effective communication plan between the project team and project stakeholders. Projects cannot succeed if there is little to no communication. The better the communication, the smoother the project will proceed and the easier it will be to understand your stakeholders’ desires. Stakeholder mapping is also a way to manage expectations. By mapping out your stakeholders, you know how they stand in regard to the project. Therefore, as the project is executed, a project manager can incrementally deal with those expectations, bringing them in line with the project so everyone is happy with the deliverables.

## HighLevelStakeholderGroups
Type | Stakeholders | Priority | High
Internal | Executive Management Team | High | Med
Internal | Senior Management Group | High | Low
Internal | Council | High
Internal | Working Group | High
External | DNSP | High
External | Small Businesses | High
Internal | Retailer | Med
External | Industry partners | Med
External | Government | Med
External | Trade associations | Med
External | The press | Med
External | All Affected Energy Consumers | Low
External | Prospective customers | Low
External | Suppliers | Low
External | Lenders | Low
External | Interest groups | Low
External | The public | Low
External | The community | Low

## StakeholderAnalysis
Stakeholder Group | Stakeholder Name | Key Interests & Issues | Current Status | Key Messages | Actions/Comms | Degree of Impact H/M/L | Degree of Influence H/M/L | Engagement approach | Frequency | Success Criteria | Owner | Notes/Comments